ACTIVITY WORKPLAN									26/05/2026 13:56:13

# Harnessing Maize Science and Innovation for Improving Food Security in Indo-Pacific

AURORA MAS Agro Nepal

# Work package 2

Agronomy and hub scoping work

# Output 2.4

Localized production system recommendations integrated with national priorities endorsed for each hub.

# ACTIVITIES 9 &10

2.4.9 Evaluate fertilizer use efficiencies for spring maize across Terai and simulate potential fertilizer savings and productivity enhancement from improved nutrient management interventions using NSAF trial data.

2.4.10 Package and disseminate fertilizer and soil health recommendations based on DSM, Soil Health Cards and crop response.

# Hypothesis

Fertilizer and soil-health advisories can improve spring maize productivity while reducing nutrient losses when they move beyond blanket recommendations and integrate crop-response evidence, soil constraints, spatial targeting, and step-wise nutrient-management innovations. The study evaluates how the innovations along an Integrated Soil Fertility Management (ISFM) continuum - from zero fertilizer and nutrient omissions to optimized rates, micronutrients, timing, organic integration, and advanced fertilizer technologies - can increase nutrient-use efficiency, reduce yield gaps, and inform localized recommendations for spring maize in the Terai.

# Target stories and Key questions

How can improved nutrient-use efficiency reduce avoidable nutrient losses while sustaining or increasing maize yield?

Where should fertilizer recommendations emphasize balanced nutrition and 4R nutrient stewardship rather than simply increasing nitrogen rates?

Where can lower nitrogen demand, improved timing, sulfur and zinc support, organic integration, or enhanced-efficiency fertilizers maintain yield without increasing nitrogen input?

Which advisory zones should be prioritized based on trial evidence, soil constraints, predicted nitrogen-use efficiency, and yield-gap potential?

How can plot-level evidence be translated into fertilizer-demand and nitrogen-saving scenarios for district, hub, and national advisory planning?

# Activity 2.4.9 Evaluate NUE, N savings and yield gains

We utilise 2017-2019 NSAF multi-year maize yield-response data to calibrate delta in efficiency of SSNM innovations and use QUEFTS nutrient-balance model to estimate N demand, considering the native N supply and soil conditions.

## Data harmonization

NSAF maize trial data from 2017-2019 form the core crop-response evidence base. Trial records are harmonized by year, site, plot identifiers, farmer identifiers, treatment codes, grain yield, fertilizer rates, and management variables.

NARC digital soil mapping data and pixel-centroid files provide spatially explicit soil pH, organic matter, macronutrients, texture, and elevation attributes.

Trial GPS coordinates are being standardised and linked to the nearest soil pixel centroid using nearest-neighbour spatial joins, allowing each trial observation to be associated with local soil and terrain properties.

## ISFM Radar: design and analytical frame

The ISFM Radar is being structured by year, treatment block, and analytical function to link the NSAF trial design directly with fertilizer advisory development. Each treatment group is being used to answer a specific agronomic question:

### Baseline diagnostics

Baseline diagnostics are being used to estimate inherent soil nutrient supply and identify the primary nutrients limiting maize yield. Absolute control plots (0-0-0) and nutrient-omission treatments, including 0-P-K, N-0-K, and N-P-0, are being compared with the government-recommended full nitrogen–phosphorus–potassium (NPK) baseline.

The analysis compares mean yield under each control or omission treatment with the full NPK baseline to estimate the yield penalty associated with nitrogen, phosphorus, or potassium limitation. This provides the diagnostic foundation for identifying where balanced fertilization is required before fertilizer-use efficiency can be improved.

YG= Ytarget=full NPK-Ybaseline=control/omission

### 4R -Rate

Rate optimization is being assessed by comparing nitrogen rates of 60, 120, 180, and 210 kg N ha⁻¹ under fixed phosphorus and potassium levels. The analysis is being used to define the nitrogen-response curve, locate yield plateaus, estimate agronomic efficiency of nitrogen, and identify where additional nitrogen produces low marginal returns.

AE-N= Yyield with nitrogen-Y0=yield without NNnitrogen rate

### 4R Timing

Nitrogen timing is being assessed by comparing the government-recommended nitrogen–phosphorus–potassium rate under conventional knee-height and shoulder-height split application with the same rate applied at V6 and V10. This isolates the effect of timing on nitrogen uptake, yield response, and nitrogen-use efficiency, while identifying schedules that maintain yield and reduce avoidable nitrogen losses.

ΔYtiming=YV6/V10 split application-Yknee/shoulder split application at same N rate

### Organic integration

The FYM integration serve different purposes. In 2018, the treatment is 6 t farmyard manure ha⁻¹ + N60-P60-K40. This treatment tests whether farmyard manure can partly compensate for reduced mineral nitrogen relative to the government-recommended N120-P60-K40 rate.

NSVreduced N=Y6 t FYM + N60-P60-K40-YN120-P60-K40 baseline

In 2019, the treatment is 6 t farmyard manure ha⁻¹ + N120-P60-K40. This treatment tests whether adding farmyard manure to the full government-recommended NPK rate provides an additional yield or soil-fertility benefit beyond mineral fertilizer alone.

FYMadded value=Y6 t FYM + N120-P60-K40-YN120-P60-K40 baseline

### 4r Source and Placement (UDP andPCU)

Polymer-coated urea and urea deep placement are being assessed as 4R source and placement options to test whether improved nitrogen release or root-zone placement can maintain yield with lower nitrogen input and improve nitrogen-use efficiency.

In 2018, the design includes two contrasts: first, urea deep placement and polymer-coated urea are compared with the N120-P60-K40 baseline at the same nitrogen rate to test source/placement effects; second, polymer-coated urea at N60-P60-K40 tests whether reduced nitrogen can maintain yield.

ΔAE-N=AE-NUDP/PCU at N120-P60-K40-AE-Nbaseline at N120-P60-K40
YPCU at N60-P60-K40≈Ybaseline at N120-P60-K40
Nsaved=Nbaseline at N120-P60-K40-NPCU at N60-P60-K40

In 2019, the nitrogen-saving assessment is conducted separately within open-pollinated variety and hybrid blocks. Within each variety type, urea deep placement at N78-P60-K40 and polymer-coated urea at N60-P60-K40 are compared with the corresponding N120-P60-K40 baseline.

YUDP/PCU reduced-N within variety type≈YN120-P60-K40 baseline within same variety type
Nsavedvariety=NN120-P60-K40 baseline within variety type-NUDP N78-P60-K40 or PCU N60-P60-K40 within same variety type

### Secondary and micronutrient support for nitrogen-use efficiency

Secondary and micronutrient integration is being assessed by adding sulfur and zinc to the standard nitrogen–phosphorus–potassium baseline. These inputs are evaluated as complementary nutrients that may relax secondary or micronutrient constraints and improve the nitrogen-response frontier.

The analysis tests whether sulfur and zinc increase agronomic efficiency of nitrogen by improving grain yield per unit of nitrogen applied, or by reducing the nitrogen required to reach a target yield.

AE-Nmicro=Yyield with NPK + sulfur/zinc-Y0 = yield without NNnitrogen rate

ΔAE-Nmicro=AE-NNPK + sulfur/zinc-AE-NNPK baseline

## Fertilizer-demand and target-yield forecasting

Nitrogen demand is being forecast for regional yield targets by combining indigenous soil nutrient supply with the optimal agronomic efficiency of nitrogen derived from the rate-response analysis. The forecast is being used to test how nitrogen requirements change under different yield targets, soil-fertility conditions, hybrid responsiveness, and moisture scenarios.

Ndemand=Ytarget yield-Y0 = indigenous soil-supply yieldAE-Noptimal efficiency

## QUEFTS mechanistic nutrient-demand modelling

The Quantitative Evaluation of the Fertility of Tropical Soils (QUEFTS) model is being used to estimate native nitrogen supply and nitrogen fertilizer demand across digital soil mapping pixels. Soil fertility, crop parameters, and weather-normal inputs are being used to generate spatially explicit nitrogen-demand estimates for comparison with NSAF trial-response evidence.

NQUEFTS=crop N demand for target yield-native soil N supplyfertilizer N recovery efficiency

## Spatial prediction, extrapolation, clustering, and machine learning

Spatial prediction will be used to extrapolate plot-level NSAF treatment-response evidence to broader maize-growing areas. Complementary approaches will be compared, including geographic interpolation, soil-covariate matching, cluster-based zoning, and machine-learning prediction. Soil, terrain, climate, and response indicators are being used to define advisory zones for targeting fertilizer recommendations.

Spatial extrapolation models (including Random Forest) trained on NSAF trial observations and DSM/NARC soil-mapping covariates, including soil pH, organic matter, macronutrients, elevation, and related spatial predictors. Will be used. The target variables include agronomic efficiency of nitrogen, with fertilizer-response potential estimated from treatment contrasts. Predicted efficiency surfaces will be combined with QUEFTS-derived nitrogen demand to identify spatial variation in response potential, nitrogen demand, yield-gap classes, and advisory zones.

AE-N=1Bb=1Bfb(Xsoil, terrain, climate)

# Validation, translation and engagement

Stakeholder engagement can be arranged after the analytical estimations are completed.

## Expert validation

- Validation will first be conducted through one-on-one expert meetings with selected agronomy, soil, extension, and hub specialists to review the plausibility of advisory-zone maps, nitrogen-demand estimates, nitrogen-use-efficiency classes, yield-gap priorities, and fertilizer-saving scenarios.

## Translation

- After validation, technical experts (extension teams, hub coordinators, input suppliers, and local planning actors) will translate the results into decision guides for the two hubs. These guides will summarize fertilizer-demand scenarios, nitrogen-saving options, and localized 4R nutrient-stewardship messages per priority advisory zones in Nepali and local languages.

## Workshop

- The wider workshop will not be used to develop the analytical outputs. Instead, it will be organized as part of broader MasAgro engagement meetings to disseminate the validated decision guides, explain their interpretation, and support uptake by hub actors and policy stakeholders.

# Timeline and budget

Once we agree on activity framing, we can come refine schedule and engagement budget.

Timeline

| Activity | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Evaluate fertilizer use efficiencies for spring maize across Terai and simulate potential fertilizer savings and productivity enhancement from improved nutrient management interventions using NSAF trial data. |  |  | 6.1 6.2 6.3 6.4 | Preliminary results | Holiday |  |  |  |  |  |
| Package and disseminate fertilizer and soil health recommendations based on DSM, Soil Health Cards and crop response |  |  | Shashis QUEFTS codeQUEFTS code | 7.1 |  | 7.1 | 7.2 | 7.3 |  |  |
| Technical report |  |  |  |  |  |  |  |  |  |  |

Budget lines

1) expert fee for 7.1 and 7.2

2) workshop for 7.3

Table 2 Design matrix table

| Year | Design step | Treatment level | Comparator level | What the comparison estimates |
| --- | --- | --- | --- | --- |
| 2017 | Soil background | N0-P0-K0 | Reference | Yield floor under no fertilizer. |
| 2017 | Add P and K without N | N0-P60-K40 | N0-P0-K0 | Yield supported by indigenous nitrogen when P and K are supplied. |
| 2017 | Recommended N response | N120-P60-K40 | N0-P60-K40 | Yield response to recommended nitrogen under adequate P and K. |
| 2017 | K omission diagnostic | N120-P60-K0 | N120-P60-K40 | Whether K limitation reduces response under recommended N and P. |
| 2017 | N-rate response | N60-P60-K40 | N0-P60-K40 | AE-N at low nitrogen rate. |
| 2017 | N-rate response | N120-P60-K40 | N60, N180, N210 | Position of recommended N rate on the nitrogen-response curve. |
| 2017 | N-rate response | N180-P60-K40 | N120-P60-K40 | Added yield response above recommended N. |
| 2017 | N-rate response | N210-P60-K40 | N180-P60-K40 | Yield plateau or diminishing returns from supra-optimal N. |
| 2017 | Micronutrient support | N120-P60-K40 + Zn + S | N120-P60-K40 | Whether Zn and S improve AE-N at the recommended N rate. |
| 2018 | Soil background | N0-P0-K0 | Reference | Yield floor under no fertilizer. |
| 2018 | Add P and K without N | N0-P60-K40 | N0-P0-K0 | Indigenous nitrogen supply under adequate P and K. |
| 2018 | Recommended N response | N120-P60-K40 | N0-P60-K40 | Yield response to recommended N. |
| 2018 | P omission diagnostic | N120-P0-K40 | N120-P60-K40 | Whether P limitation reduces response under recommended N and K. |
| 2018 | K omission diagnostic | N120-P60-K0 | N120-P60-K40 | Whether K limitation reduces response under recommended N and P. |
| 2018 | 4R timing baseline | N120-P60-K40 at knee/shoulder | Reference for timing | Conventional timing benchmark. |
| 2018 | 4R timing | N120-P60-K40 at V6/V10 | N120-P60-K40 at knee/shoulder | Timing effect at the same N rate. |
| 2018 | FYM with reduced N | 6 t FYM + N60-P60-K40 | N120-P60-K40 | Whether FYM partly compensates for reduced mineral N. |
| 2018 | UDP at recommended N | UDP N120-P60-K40 | N120-P60-K40 | Placement effect on AE-N at the same N rate. |
| 2018 | PCU at recommended N | PCU N120-P60-K40 | N120-P60-K40 | Controlled-release source effect on AE-N at the same N rate. |
| 2018 | PCU reduced N | PCU N60-P60-K40 | N120-P60-K40 | Whether PCU maintains yield with half the N rate. |
| 2018 | PCU rate comparison | PCU N60-P60-K40 | PCU N120-P60-K40 | Whether full-rate PCU gives added yield over reduced-rate PCU. |
| 2019 | OPV N benchmark | OPV N120-P60-K40 | Reference within OPV | OPV-specific full NPK baseline. |
| 2019 | OPV FYM with full N | OPV 6 t FYM + N120-P60-K40 | OPV N120-P60-K40 | Added value of FYM beyond full NPK in OPV maize. |
| 2019 | OPV Zn support | OPV ZnSO₄ + N120-P60-K40 | OPV N120-P60-K40 | Whether Zn improves AE-N under full NPK in OPV maize. |
| 2019 | OPV UDP reduced N | OPV UDP N78-P60-K40 | OPV N120-P60-K40 | Whether UDP maintains OPV yield with reduced N. |
| 2019 | OPV PCU reduced N | OPV PCU N60-P60-K40 | OPV N120-P60-K40 | Whether PCU maintains OPV yield with reduced N. |
| 2019 | Hybrid N benchmark | Hybrid N120-P60-K40 | Reference within hybrid | Hybrid-specific full NPK baseline. |
| 2019 | Hybrid FYM with full N | Hybrid 6 t FYM + N120-P60-K40 | Hybrid N120-P60-K40 | Added value of FYM beyond full NPK in hybrid maize. |
| 2019 | Hybrid Zn support | Hybrid ZnSO₄ + N120-P60-K40 | Hybrid N120-P60-K40 | Whether Zn improves AE-N under full NPK in hybrid maize. |
| 2019 | Hybrid UDP reduced N | Hybrid UDP N78-P60-K40 | Hybrid N120-P60-K40 | Whether UDP maintains hybrid yield with reduced N. |
| 2019 | Hybrid PCU reduced N | Hybrid PCU N60-P60-K40 | Hybrid N120-P60-K40 | Whether PCU maintains hybrid yield with reduced N. |