Future-proofing Indo-Pacific Agrifood Security

Designing and Implementing AI-driven Predictive Wheat and Maize Breeding and Agronomic Management in South Asia

CIMMYT-BISA Concept Note for Aurora Investment: 30 January 2026

- Rationale

Crop productivity in the Indo-Pacific region is constrained by various challenges, including inappropriate management of water and nutrients, recurring biotic and abiotic stresses, etc., affecting roughly 2 billion people in South Asia alone. Moderate or severe food insecurity remains the highest among all subregions in South Asia (FAO, IFAD, WHO and WFP, 2025). These complex challenges need to be addressed through effective amalgamation of genetic and non-genetic innovations, powered by digital innovations and analytical tools. Artificial Intelligence (AI) is renowned for its prowess in big data analysis and pattern recognition and is revolutionizing numerous domains including agriculture and agricultural research. AI has emerged as one of the pivotal tools for driving innovations in agricultural research for improving productivity and sustainability. AI-enabled tools can optimize breeding strategies, cropping systems, enhance resource use efficiency, productivity improvement, and effectively manage pests and diseases.

Crop breeding is undergoing a profound digital transformation, evolving from traditional hybrid breeding to molecular breeding and then to smart breeding (Zhang et al., 2025). Recent advances in high-throughput phenotyping (HTP) platforms, including unmanned aerial vehicles (UAVs), ground-based sensors, and multispectral imaging systems, have the potential to enable rapid, non-destructive monitoring of crop performance across large experimental and production landscapes. These platforms generate large volumes of data, but extracting actionable information from such datasets exceeds the capacity of traditional analytical approaches. Machine learning (ML) or Deep Learning (DL) can enable analysis of vast datasets (genomes, phenotypes, environment) to identify optimal gene combinations and predicting plant performance before field trials. This approach ensures rapid, precise development of traits like drought tolerance, heat tolerance, disease resistance, and higher nutritional value. ML-driven stress phenotyping can improve screening efficiency, accelerate breeding cycles, and support timely management decisions, directly contributing to yield stability and production efficiency in maize and wheat breeding in South Asia.

Similarly, timely analysis of huge agronomic data sets from diverse agroecologies with significant spatio-temporal variations is important for translation of research into context-specific solutions. There is a need to take CIMMYT-BISA’s agronomic research in South Asia to the next level, using emerging tools of big data analytics, geo-referenced satellite information, UAV-based imaging, and AI-based techniques. This can help in integrating diverse data streams, including crop performance data, weather data, soil reports, and historical records, for more informed decision-making on cropping systems diversification and transformation of agrifood systems in South Asia.

Research institutions across South Asia have not yet tapped the huge potential of AI in various facets of agricultural research, including predictive breeding, and crop management. The critical barriers include inadequate understanding of the tools/technologies, limited access to high-quality data, lack of reliable, context-specific data for AI model training and/or interoperability, lack of institutional coordination, data privacy concerns, regulatory uncertainty etc. The proposal aims to address this critical gap in agricultural R4D in South Asia through the establishment of Digital Agricultural Innovation Hubs in South Asia that can evaluate/validate predictive breeding and precision agriculture models, demonstrate practical, data-driven breeding and agronomic management, and train next generation of researchers.

2. Value Proposition

CIMMYT-derived wheat and maize germplasm have demonstrated impacts in South and SE Asia. For instance, in India, six of the top 10 wheat varieties occupying the highest acreage are CIMMYT-related. The value proposition of this project centers on accelerating the development of superior varieties by transforming breeding from an observation-based, time-consuming, and labour-intensive process into an efficient, data-driven, and predictive discipline. By utilizing ML/DL, breeders can analyse massive datasets—genomic, phenomic, and environmental—to make faster, more accurate selection decisions, thus significantly improving the efficiency, and reducing the time required for conventional breeding. Similarly, by leveraging ML, computer vision, and IoT, AI can optimize inputs (especially water and fertilizers), maximize yield, reduce costs of cultivation, and enhance sustainability. The market for AI-driven precision agriculture is rapidly growing, with AI-driven precision agriculture as it is expected to increase yields by 15–30% and reduce resource inputs by up to 60%.

Thus, through this investment, CIMMYT-BISA has an excellent opportunity to demonstrate the power of AI-driven research in crop breeding and management, improve the efficiency of our impactful wheat and maize breeding programs, and more effectively leverage data from our historical/ongoing breeding trials and long-term agronomic trials. This, in turn, is expected to place CIMMYT-BISA as a major thought leader and a “go-to partner” on data-driven crop breeding and precision agriculture.

- Core Objectives

Objective 1: Establish and operate Digital Agricultural Innovation Hubs at the BISA Research Stations in India as platforms for strategic and applied research and capacity building.

Objective 2: Improve the efficiency and impact of wheat and maize breeding in South Asia by integrating AI with high-throughput phenotyping, doubled haploidy/rapid generation advancement, and genomic selection.

Objective 3: Create AI-powered and evidence-based agronomic decision support systems for optimizing resource use and cropping system diversification in South Asia

Objective 4: Strengthen regional capacities on AI-driven crop breeding and agronomic management.

- Alignment with CIMMYT 2030 Strategy, and US Government Priorities

In the CIMMYT 2030 Strategy, in addition to strengths and opportunities, several critical gaps in CIMMYT’s capacity have been identified which need to be addressed in order to effectively implement the Strategy. To quote: “Firstly, we need to significantly strengthen our capabilities on data management, bioinformatics, analytical platforms and deep/machine learning… These capabilities will help position the Center to leverage new technologies in our work including by streamlining market intelligence information from diverse sources and effectively aligning it with the breeding and seed systems priorities. Furthermore, we need to improve our capability to develop impactful products using disruptive innovations (e.g., genome editing, predictive breeding). Delivering cutting edge science into the hands of smallholder farmers in the global south is at the core of CIMMYT’s competitive advantage and this must be prioritized.” (p.20).

The proposed work aligns closely with CIMMYT Strategy 2030 by advancing all three pillars: Discovery, SystemsDev, and Inc. The multi-disciplinary CIMMYT-BISA team will help in greater integration of the research strengths and complementarities of the two institutions, while simultaneously strengthening CIMMYT-BISA’s role as a major partner for AI-driven R4D, and as a catalyst for agricultural research transformation.

Primary users of the outputs from this investment include national governments, scientists, post-graduate students at partner institutions, and over a period of time SMEs doing agricultural R&D. The ultimate beneficiaries extend beyond the adopters to include rural communities, and ecosystems that provide critical services in agricultural research.

The U.S. government, through the USDA and NSF, has made accelerating AI in agriculture a strategic priority to increase production by 40% while cutting the environmental footprint in half by 2050. Federal priorities focus on sustainable, climate-smart agriculture, labor automation, and enhancing decision-making for farmers through "AI-ready" datasets and "living labs". The objectives of the present project strongly align with the key US Government Strategy/Initiatives, including the USDA AI Strategy (FY2025–2026), and some of the core activities of the National AI Research Institutes for Agriculture.

- Geographic Focus

The project will focus on South Asia (especially India and Nepal), with potential spillover effects in South East Asia (e.g., Indonesia, Philippines). Major part of the research work will be implemented at CIMMYT-BISA research stations/field sites at five selected hubs in South Asia. Digital Agricultural Innovation hubs will be established at the Borlaug Institute for South Asia (BISA) at its well-established research stations in Ludhiana (Punjab), Pusa (Bihar), and Jabalpur (Madhya Pradesh), representing three major agroecologies in India. These stations include secured land, experimental blocks, irrigation infrastructure, seed storage infrastructure, training facilities, guest houses, etc. The stations will serve as the physical platforms for deployment and demonstration of IoT- and AI-enabled digital agriculture infrastructure.

The hubs will serve as strategic research, technology demonstration, and capacity building platforms, showing how field-level digital infrastructure and AI-driven analytics can improve predictive breeding, and support timely agronomic management actions. The hubs will be potentially replicable and scalable in different countries in the Indo-Pacific region. The proposed Digital Agricultural Innovation Hubs will be dynamically linked to CIMMYT Headquarters in Mexico for data management, including storage and analytics. The geographic focus spans cereal-based systems, especially maize and wheat, across India, Nepal and Bangladesh in South Asia, with potential spillovers to targeted countries in SE Asia, especially Indonesia and the Philippines.

- Work Packages, Key Activities, and Outputs

WP1: Establishment of Digital Agricultural Innovation Hubs at BISA Research Stations in India as platforms for strategic and applied research and capacity building

The main aim of establishing the three Digital Agricultural Innovation Hubs at the BISA Research Stations in India is to undertake high-quality R4D on high-throughput field-based phenotyping (for relevant abiotic and biotic stresses of wheat and maize) and precision agriculture in different agroecologies. These platforms will serve as “living labs” that will help leverage multi-layered datasets for implementing the work proposed in the other Work Packages. These Innovation Hubs will support not only the work of scientists and young post-graduate students, but will also demonstrate to the policy makers, farmers and other value chain actors the power of digital tools/technologies in modern agricultural research, and shall accelerate further development and uptake of digital innovations.

Another major purpose of the Digital Agricultural Innovation Hubs is to effectively link CIMMYT Discovery and SystemDev with CIMMYT Inc in South Asia. The hubs can serve multiple functions in this regard: a) Engage start-ups, established companies and various end-users into CIMMYT-BISA R4D ecosystem; b) Utilize our well-established physical infrastructure (training centers, guest houses) to conduct relevant meetings/workshops; and c) foster cooperation between innovation stakeholders and responsible sourcing partners.

Key activities:

- Procurement of sensors (soil moisture, pH, temp), cameras/drones, and edge computing devices.

- Building digital infrastructure for data sharing, interoperability of systems, and secure data access.

- Hiring relevant staff/consultants with expertise in data science, AI, ML/DL, and robotics.

- Establish partnerships with public and private sector institutions having the best expertise in precision agriculture and predictive breeding.

- Partnerships with relevant Universities in India so that these platforms are dynamically used by at least 10 post-graduate students (at least 50% female) at any given time for undertaking relevant research programs.

Outputs: Digital Agricultural Innovation Hubs established at the three BISA Research Stations with necessary infrastructure and manpower; MoUs signed with at least 2-3 private sector partners for further strengthening the Innovation Hubs; MoUs signed with at least 3-4 major research institutions/Universities in India for collaboration through post-graduate students.

WP2: Improve the efficiency and impact of wheat and maize breeding in South Asia by integrating AI with high-throughput phenotyping, doubled haploidy/rapid generation advancement, and genomic selection.

AI-driven maize and wheat breeding at CIMMYT-BISA hubs in South Asia represents a critical step toward future-proofing food security in the Indo-Pacific region. AI, doubled haploidy (in maize), rapid generation advancement (in wheat), high-throughput field-based phenotyping, and genomic selection can be effectively combined to modernize wheat and maize breeding in South Asia. Integrating genomic and environmental data generated by CIMMYT-BISA team at various locations in India can result in an automated ML framework for improved accuracy and efficiency in genetic analyses and genomic predictions (He et al., 2025). Ultimately, this whole approach will reduce breeding cycles, increase breeding efficiency, and lower product development costs.

Key activities:

- Standardize historical data, set-up database ontology, and train initial ML models.

- Utilize UAV (drone) imagery and computer vision (CNNs) to automate field phenotypic assessments for key agronomic and adaptive traits in maize and wheat breeding.

- Deploy AI-powered apps (like ImageSafari) for field-based teams to collect objective, real-time data.

- Implement Random Forests (RF) and Support Vector Machines (SVM) to analyse complex genomic data and genotype-by-environment (GxE) interaction data to predict hybrid maize performance for grain yield and abiotic (drought/heat) stress tolerance and biotic stress resistance (e.g., TLB, PFSR).

- Train AI models on historical wheat breeding records and diverse datasets to ensure robustness and biological accuracy.

- Using genomic and multi-location performance data, train AI-based predictive models to increase the precision of genomic selection in maize and wheat, optimizing parental line selection in hybrid breeding.

- Use predictive models to select the most promising maize DH lines, and wheat genotypes for targeted development and testing of hybrids in specific agroecologies in India and Nepal.

Outputs: Operational frameworks set-up for smart and data-driven breeding systems for maize and wheat in South Asia; Enhanced use of AI-powered apps in wheat and maize breeding reducing manual errors; Predictive algorithms available for optimized parental line selection and hybrid development.

WP3: AI-powered and Evidence-based Agronomic Decision Support Systems for South Asia for Improving Resource Use Efficiency

There is an urgent need for an automated, data-driven approach to transform agronomic practices from reactive to proactive, especially in climate-sensitive regions. The project proposes to design and implement an evidence-based, AI-powered integrated agronomic decision support systems leveraging historical data, IoT sensors and computer vision to monitor, analyse, and manage water and nutrient management, and crop health (Aijaz et al., 2025). The models for such systems will be initially established at the three BISA research stations in India. These, in turn, will provide actionable and scalable insights and models for implementation in diverse agroecologies in South Asia, especially in India and Nepal.

Key activities:

- Establish a real-time monitoring system using IoT sensors and drone imagery for constant, granular field monitoring (soil moisture, temperature, nutrients) at the BISA Research Stations.

- Implement AI-driven irrigation and fertilization schedules at the BISA research stations to reduce water and nutrient wastage.

- Utilize long-term trial datasets to develop ML models (Random Forest, LSTM) to optimize agronomic management practices, and cropping systems diversification for different agroecologies.

Outputs: Real-time agronomic and soil health monitoring system established at BISA Research Stations; AI-driven irrigation and fertilization schedules developed; Long-term trial datasets analyzed and ML models developed for predictive analytics; A White Paper on potential applications of AI in the context of South Asia for optimized resource use and for improving sustainability together with productivity.

WP4: Strengthening Regional Capacities on AI-driven Crop Breeding and Management

One of the crucial outputs of the project is enhanced capability of national partners in targeted countries in South Asia (India, Bangladesh, Nepal) and SE Asia (Indonesia, Philippines) on AI-driven breeding and crop management. This work package will be cross-cutting, with all the other work packages contributing to capacity building of participants, including female, male and young scientists, in relevant areas.

Key activities

- Utilize Digital Agricultural Innovation Hubs of BISA as platforms for hosting post-graduate students from partner institutions in India (and if possible, Nepal) for undertaking research on identified areas.

- Conduct national and regional training workshops on AI-powered maize/wheat breeding and crop management.

- Exchange visits of CIMMYT-BISA core team to relevant institutions in the USA, and Australia for establishing collaborative research.

Outputs: At least 10 post-graduate students initiate research work on relevant areas at the Digital Agricultural Innovation Hubs; Two Regional Training Workshops organized on AI-driven crop breeding and management; At least three advanced research institutions in the USA and Australia sign MoUs with CIMMYT-BISA for strategic partnerships on the project.

WP5: Data Management, MEL, Communication, and Project Management

Data management, Monitoring, Evaluation, and Learning (MEL), Communication, and Project management are cross-cutting enablers that ensure effective implementation of the project, institutional learning, and appropriate outreach to different stakeholders. MEL elements shall be embedded throughout the project to track the milestones, remove bottlenecks, and incentivise performance. Communications team shall translate the key technical findings into actionable insights to the investor as well as national partners, including policy makers.

Key activities:

- Establish an integrated data management and MEL system to effectively utilize historical and project-generated datasets (pedigree, genomic, phenotypic, agronomic, weather data).

- Design and implement an appropriate communication strategy appropriate for the project, so that technical deliverables are communicated in an understandable and action-oriented findings to diverse stakeholders.

- Periodic project management meetings (online and in-person) to ensure strong linkages among the geographically dispersed and multi-disciplinary teams

- Formulation and submission of high-quality technical reports and briefing notes.

Outputs: An integrated data management system with necessary security; MEL dashboard for tracking KPIs relevant for the project; Communication products appropriate for different audience/stakeholders; Project technical and financial reports; News stories linked to key project events and publications; Social media promotion of project activities; Short video to highlight the work on the project and use for advocacy.

- Project Milestones in 2026

- Establishment of Digital Innovation Hubs at the three BISA Research Stations in India, with necessary infrastructure and manpower (by Sept 2026).

- Genome-phenome datasets on core CIMMYT maize and wheat germplasm analysed for developing predictive models (by Sept 2026)

- Long-term agronomic trial data analysed for developing ML/DL models (by Sept 2026).

- An AI-based DRAFT predictive framework developed in maize for analysis of heterotic patterns, heterosis estimation and hybrid performance prediction using historical genomic and phenomic data generated by CIMMYT for further validation (by October 2026).

- An AI-based DRAFT predictive framework developed in wheat for parental selection in breeding programs to bring in superior allelic/haplotype combinations for desired traits in South Asia (by October 2026).

- Improved access to real-time, site-specific agronomic information generated at the Digital Innovation Hubs (by November 2026)

- Two Regional Workshops organized to highlight the relevance and benefits of AI-driven predictive crop breeding and agronomic management in South Asia (by November 2026).

- At least 5-6 post-graduate students (including female and male students) from national partner institutions trained in AI-driven crop breeding and management (by December 2026).

- Pathway for Further Resource Mobilization

Investment in this pilot project will enable CIMMYT-BISA team to potentially formulate expanded research projects to source additional financial resources through international and national funding agencies, including: a) US State Department; b) Gates Foundation (in India); c) Asian Development Bank; d) NABARD (National Bank for Agriculture and Rural Development) in India; e) Private sector institutions (e.g., TAFE, Jain Irrigation), etc. Discussions are already being held with TAFE and Jain Irrigation on support for modernizing the BISA research stations. AI is one of the important Big Bets of the new strategy of the Gates Foundation globally and in Asia.

COMMS and DFS will help in building the visibility and investment pipeline needed to deliver ouputs beyond the project period by translating technical results into compelling communication products for donors, policy makers, and private-sector partners. DFS and CIMMYT Inc will convene strategic engagement with key partners (both public and private) to co-develop follow-on proposals and co-investment pathways. Further resource mobilization is expected to lead to several key outputs, such as those outlined below, in subsequent years (2027-2028).

- Shifting from traditional, experiential breeding to intelligent, data-driven, maize and wheat breeding that require fewer inputs, and offer stable yields under climate instability.

- Increased efficiency and timeliness of data generation and processing from the Digital Innovation Hubs in India and Nepal.

- Deeper understanding of breeding values and heterotic patterns in Asia-adapted CIMMYT maize germplasm, which can possibly benefit US Corn Belt breeding programs through temperate-tropical introgression.

- Optimized parental line selection leads to targeted product development through wheat breeding in South Asia.

- AI-driven maize and wheat breeding capability of researchers across the Indo-Pacific region, especially in South and SE Asia, strengthened.

- High-impact publications on AI-driven predictive breeding and crop management, especially in South Asia.

Long-term Impact

The long-term impact of AI-driven predictive crop breeding and agronomic management in South Asia is a fundamental, structural transformation of agriculture from a reactive, labor-intensive industry to a proactive, data-driven, and precise ecosystem. This shift is designed to secure the food supply for a rapidly growing population in the Indo-Pacific region while simultaneously addressing environmental sustainability, climate change, and resource scarcity.

- AI-powered digital innovation hubs simulate maize and wheat breeding outcomes at both CIMMYT-BISA and partner institutions to identify superior allelic combinations for drought tolerance, disease resistance, enhanced nutritional quality, and other traits of value to the farming communities and agri-industry.

- AI-driven precision agriculture reduces water usage by up to 30%, fertilizers by 20–30%, and pesticide applications by 20–40% in South Asia.

- Next-generation researchers in Asia (trained through this project) implement AI-driven crop breeding and management in their respective national institutions driving further growth.

- Proposed CIMMYT-BISA Team, and Strategic Partnerships

- The CIMMYT-BISA core research team shall include B.M. Prasanna, Prasun Gandopadhyay, Velu Govindan, Pradeep Bhati, Ashish Saxena, PH Zaidi, Mainassara Zaman-Allah, Rajkumar Jat, Mahesh Gathala, Alison Laing, and Abhishek Rathore, bringing together multi-disciplinary expertise including wheat and maize breeding, digital agriculture, biometrics, stress phenotyping, agronomy, and systems research.

- CIMMYT-BISA Communications team in the region (Nima Chodon, Richa Sharma Puri) will provide necessary support, by bringing out high-quality communication and knowledge products, besides necessary visibility.

- BISA-CIMMYT Operations Chapter Team will help in organization of regional training/capacity building workshops at the BISA Research Stations.

- Strategic partners will include ITC, TAFE, Jain Irrigation, University of Nebraska-Lincoln, and QAAFI-Advanced Center for Predictive Breeding.

Cross-Institutional and Cross-Program Integration and Contributions

| Program | Major responsibilities | Estimated Budget (USD) |
| --- | --- | --- |
| BISA | Establishing Digital Agricultural Innovation Hubs (WP1); Interface with GWP and GMP on AI-driven breeding (WP2); Interface with SAS on AI-driven precision agriculture; Organizing regional/national capacity building activities (WP4); Interface with MEL, COMMS, DATA and DFS (WP5); Project management and coordination with internal and external partners (WP5) |  |
| GWP | Establishing and operating HTP platform for relevant abiotic/biotic stresses in wheat; AI-driven wheat breeding using appropriate datasets (WP2); Organizing regional/national capacity building activities (WP4) |  |
| GMP | Establishing and operating HTP platform for relevant abiotic/biotic stresses in maize; AI-driven wheat breeding using appropriate datasets (WP2); Organizing regional/national capacity building activities (WP4) |  |
| SAS | Agronomic support for establishing Digital Agricultural Innovation Hubs at BISA research stations (WP1); AI-driven crop management using appropriate datasets (WP2); Organizing regional/national capacity building activities (WP4) |  |
| DATA | Data management and processing framework and standards set-up; optimizing computational resources; support for preprocessing and processing. | 200,000 |
| MEL | KPI development and monitoring, including indicators, data flows, tools, learning cycles, and setting up relevant dashboards/templates | 75,000 |
| COMMS | Donor-ready technical briefs/flyers; News stories linked to key project events; Social media promotion of project activities; Brief videos highlighting project work. | 50,000 |
| DFS | Resource mobilization, including targeted donor engagement, and follow-up on funding pipelines | 75,000 |

- Budget (USD)

| Line Item | Description | Estimated Cost (USD) |
| --- | --- | --- |
| CIMMYT-BISA Personnel | 10 FTEs (Scientific leadership for different WPs, Data analytics, Communication, Project coordination) | 1,500,000 |
| CAPEX | Digital infrastructure and Sensors relevant for establishing the Digital Agricultural Innovation Hubs at the BISA Research Stations | 750,000 |
| Operational costs | Field experiments and data collection; Field/lab/office consumables | 500,000 |
| Consultants | 4 consultants, with strong expertise on Digital Agriculture, AI, HTP, Genomic Selection @USD 2,500/month/consultant × 9 months | 90,000 |
| Subgrants to Strategic Partners | Potential strategic partners in India (e.g., ICAR, Piatrika Biosystems, Valyria Visions), Nepal (NARC), USA (Iowa State Univ., Univ. Nebraska-Lincoln), and Australia (QAAFI-ARC Center on Predictive Breeding) | 200,000 |
| Travel (International & Regional) | India, Nepal, Mexico, USA, Australia | 75,000 |
| Regional Workshops (2) | India, Nepal | 80,000 |
| Data management | Data management and processing; Cloud services; Optimizing computational resources | 200,000 |
| MEL | KPI development; Progress tracking | 50,000 |
| Communication & Knowledge Products | Technical briefs/flyers, Brief videos | 35,000 |
| Miscellaneous & Contingency | Inflation, exchange-rate variation | 20,000 |
| Subtotal | Direct costs | 3,500,000 |
| CIMMYT Overhead | 15% | 525,000 |
| Grand Total |  | 4,025,000 |

Note: BISA costs are embedded in the above-mentioned line items. These will be further segregated for sub-granting from CIMMYT.

11. References Cited

Aijaz N, Lan H, Raza T, Yaqub M, Iqbal R, Pathan MS (2025) Artificial intelligence in agriculture: Advancing crop productivity and sustainability. Journal of Agriculture and Food Research 20: 101762. https://doi.org/10.1016/j.jafr.2025.101762

FAO, IFAD, WHO and WFP (2025) Asia and the Pacific Regional Overview of Food Security and Nutrition 2025 – Accelerating actions for agrifood systems transformation for food security and better nutrition. Asia and the Pacific – Regional Overview of Food Security and Nutrition, 2025. Rome. https://doi.org/10.4060/cd7666en

Farooq MA, Gao S, Hassan MA, Huang Z, Rasheed A, Hearne S, Prasanna B, Li X, I H (2024) Artificial intelligence in plant breeding. Trends in Genetics 40(10): 891-908. https://doi.org/10.1016/j.tig.2024.07.001

He K, Yu T, Gao S, Chen S, Li L, Zhang X, Huang C, Xu Y, Wang J, Prasanna B, Hearne S, Li X, Li H (2025) Leveraging automated machine learning for environmental data-driven genetic analysis and genomic prediction in maize hybrids. Advanced Science 12: 241243. https://doi.org/10.1002/advs.202412423.