## SAS - Agronomy & Scoping
No | Output | Activity | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec
1 | A strategic roadmap for effective implementation of the hub model established with public and private sector stakeholders | Conduct Nepal MasAgro maize hub maize scoping assessment using Integrated Agrifood System Initiative (IASI) tool | bar: April to July
Conduct Hub-visioning and planning workshops in each hub | bar: April to July
Strengthen the structure and design of the hub platforms, farmer modules, extension areas, multi stakeholder platforms and market segments for establishing hub model. | bar: May to Aug
2 | Two hubs in Western and Eastern Nepal established with functional management and governance structures with a focus on maize and wheat | Launch the two hubs in Western and Eastern terai in collaboration with the MoALD, NARC and other public and private actors | bar: Sep
Establish Research and Development platforms with NARC | bar: April to June; Sep to Nov
Link/Align hubs with MoALD programs | bar: May; Sep to Nov
Organize High level visits to MCM hubs | bar: May; Oct to Nov
Co- develop curricula for hub level extension and farmers training | bar: May; Oct to Nov
Organise training for hub level actors | bar: June to Nov
Conduct quarterly Hub meetings | bar: June to Nov
3 | About 20,000 women, men, and young farmers, in proportions reflective of their population sizes, benefit from improved maize production technologies and market development. | Support farmers to prepare maize production plans | bar: March to April
Establish multi stakeholder platforms | bar: March to May
Facilitate investment roadmaps for seeds, soil fertility, mechanisation | bar: March to May
Organise TOTs for farmers, input dealers, MSMEs utilizing hub level demonstration sites | bar: March to July
Facilitate farmer market linkages | bar: May to July
4 | Localized production system recommendations integrated with national priorities endorsed for each hub.
Test and validate innovative technologies such as precision/pneumatic planters, zero tillage, intercropping, farm machinery etc for incorporating in national level maize extension system | bar: March to May; Sep to Nov
Workshop on hub level Agronomy and Irrigation | bar: Aug
Workshops on hub level Mechanisation to evaluate suitability and co-design innovative service delivery and business models | bar: Sep
Workshops on hub level market and industrial linkages | bar: Aug
Prepare report on production recommendations | bar: Sep to Oct
Prepare report on hub level research agenda | bar: Sep
Prepare dissemination strategy by linking research with extension systems | bar: Aug to Nov
Compile agronomic and economic indicators' values from selected demonstration plots across Hubs and analyze them for preparing recommendations | bar: Aug to Nov
Evaluate fertilizer use efficiencies for spring maize across Terai and simulate potential fertilizer savings and productivity enhancement from improved nutrient management interventions using NSAF trial data. | bar: March to Aug
Package and disseminate fertilizer and soil health recommendations based on DSM, Soil Health Cards and crop response | bar: Aug to Nov
5 | Package of practices for maize postharvest management and value addition piloted and recommendations for use by farmers groups and micro small and medium enterprises prepared | Pilot maize drying with feed mills | bar: March to June
Pilot threshing, drying, grain storage and silage with key staleholders | bar: May to July
6 | Digital platforms for monitoring hub level innovation use and application of precision technologies tested and implementation modalities finalized with stakeholders. | Establish the e-agrology model | bar: March to June; Aug to Nov
Develop sustainability standards | bar: June to Aug
Develop a digital extension strategy for the hubs | bar: May to Nov
Conduct cost benefit analysis of improved technologies using data from e-agrology platform, technology trial and demonstration sites | bar: May to Nov
7 | RM, COMMS, M&E and reporting | Finalise indicators with CIMMYT MEAL team | bar: March to April
Reporting | bar: March; June; Sep; Dec
Proposal development

## GMP-Breeding & Seed System
No | Output | Activity | Target | March | April | May | June | July | Aug | Sep | Oct | Nov | Dec
1 | Climate similarity maps and product profiles validated | Develop climate similarity maps & product profiles for Nepal | At least 3 priority agro-ecologies mapped | bar: Nov to Dec
2 | 15–20 validation/demo sites established | Conduct participatory varietal validation trials | 15-20 sites with farmers and organize at least three FFD to document farmers choices | bar: Aug to Dec
3 | At least two new stress tolerant hybrids advanced for licensing or variety registration | Advance hybrid varieties toward release | At least two new stress tolerant hybrids | bar: April to Sep
4 | Improved seed company technical capacity in monitoring and maintaining seed quality | Strengthen seed company capacity and their technical staff | 8-10 private seed companies supported and 20-30 people trained on quality hybrid seed production. At least one joint field monitoring visit conducted to hybrid production sites with key stakeholders. | bar: Oct to Dec
5 | Nepal Coordinated Maize Evaluation Network (NCMEN) Initiated | Establish coordinated varietal testing platform with the participation of public (NARC, SQCC....) and private stakeholders (seed companies, SEAN...) | One national platform | bar: April
6 | Hub-based seed systems platforms operational | Establish PPP seed business incubation platforms | Two hubs supported in Dang and Nepalgunj districts | bar: April; Dec
7 | DESIS 2.0 system operational and adopted | Promote the new features of DESIS 2.0 and conduct orientation trainings | 30-35 key stakeholders including seed inspectors, seed analysts trained in collaboration with SQCC | bar: April to May; Aug to Sep; Dec
8 | Hub-level seed roadmap endorsed | Develop hybrid maize seed roadmap for demand estimation and create partnership | Two hub-level roadmap developed | bar: April to Aug; Dec
9 | Functional EGS hub with improved facilities | Upgrade Nepalgunj seed hub with cold store, irrigation systems and land levelling | Construction of a seed store with the capacity of 15-20 MT for EGS storage