## Activity Level
Work Package | Key Activity | Deliverable/Outputs | Activity lead FTE) | Contributors FTE) | FTE estimate IRS- NRS- | Supplies and Services US$) | Partners grant)/ consultant fee) US$) | Co-Financing in 2026 US$) | Co-Financing donor | Possible Future Funding Source &US$) | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Overall | 31 | 27 | Dyutiman (...)
Work package 1: Strengthening Regional and Scientific Cooperation |  |  | GMP: Zaidi
Work package 1: Strengthening Regional and Scientific Cooperation | 1.1 Mapping maize mega-environment in Indo-Pacific and develop climate-similarity mapping for targeted development, deployment and delivery of weatherproof maize technologies | 1.1 Map of major maize mega-environments in the Indo-Pacific region, along with climate similarity mapping for effective and efficient multilocation testing for the stage-gate advancement process. | Zaidi | Powell, Maxwell, Sreejith | [6 empty] | Feb: Design; Mar: Design, Data; Apr: Data, Model; May: Model, Analysis; Jun: Report; Aug: Validation; Sep: Revision
Work package 1: Strengthening Regional and Scientific Cooperation | 1.2 Designing mega-environment specific product profiles for Indo-Pacific region for targeted breeding of best-suitable high-yielding maize with stable performance under variable weather conditions. | 1.2 Agroecoregion-specific maize product profiles for various agro-ecologies in Indo-Pacific with a trait matrix of defined MUST-HAVE and GOOD-TO-HAVE trait profiles. | Zaidi | Abdu, LRS
Work package 1: Strengthening Regional and Scientific Cooperation | 1.3 Collate research backed evidence on the equitable livelihood and food security benefits of maize-based diversified farming systems for households headed by women, men, and young people in Nepal and India for generating investments and facilitating policy decisions on promoting diversified maize-based farming. | 1.3 One technical report on livelihoods benefits from diversified maize based systems prepared | Adeeth | Ravi, Dyutiman, Bharathi , Narayan | 10500 (Adeeth) | 1500 (Adeeth) | NA | NA | NA | NA | Feb: Data cleaning; Mar: Data analysis; Apr: Draft paper/report; May: Draft paper/report; Jun: Review; Jul: Review; Dec: Paper/report published
Work package 1: Strengthening Regional and Scientific Cooperation | 1.4 Forge strategic research partnerships and exchange on maize sector improvement with ACIAR, KOICA and JICA through exchange programs, joint assessments and new project development. | 1.4 A report on strategic engagement for regional and national maize sector improvement developed with ACIAR, KOICA and JICA. | Dyutiman | Mahesh, Owen , Alison, Ravi, Amjath, Powell, Zaidi, Abdu
Work package 2: Farm Productivity Improvement |  |  | Mahesh
Work package 2: Farm Productivity Improvement | 2.1 Deriving new maize hybrids from genomic-assisted product pipelines, early generation evaluation in delineated maize zone for respective profile and multilocation evaluation for stage-gate advancement process | 2.1.1 A set of stage-1 crosses evaluated across locations in S & SE Asia at best representative sites for further advancement through stage-gate process. 2.1.2 At least two trainings-cum-workshop on genomic-assisted accelerated breeding organized for NARS partners in the region, and training module developed for open-access platform. | Zaidi | Abdu
Work package 2: Farm Productivity Improvement | 2.2 Widening the CIMMYT maize network in Southeast Asia, especially Indonesia, Laos, Myanmar & Philippines, by developing, testing and delivering high-yielding stress-adaptive maize hybrids and associated breeding technologies in partnership with NARS. | 2.2 A set of advanced-stage stress-resilient maize hybrids from CIMMYT-Asia maize program tested in Southeast Asian countries, and first batch of potential hybrids identified for the region. | Zaidi | Abdu
Work package 2: Farm Productivity Improvement | 2.3 Integrate doubled-haploid (DH) technology in NARS & SME breeding pipeline by providing DH service from CIMMYT’s DH facility at Kunigal, India as well as technical know-how | 2.3 Doubled haploid lines (close to 5000) developed at CIMMYT’s DH facility in India from an estimated 50 maize populations of collaborating NARS in South and South East Asia primarily from India and Philippines NARS and made available for fast-tracking their breeding program with reduced breeding cycle time. | Zaidi | Abdu
Work package 2: Farm Productivity Improvement | 2.4 Product announcement and licensing for commercialization and pre-release validation through on-farm participatory testing with women, men, and young farmers selected with probability sampling methods, where feasible. | 2.4 At least two robust weatherproofing maize hybrids identified for each targeted country in the region and formally announced for licensing at CIMMYT website. | Zaidi | Abdu
Work package 2: Farm Productivity Improvement | 2.5 Develop spatial seasonal maize yield gap analysis and seasonal maize cultivation suitability mapping across South and Southeast Asia. | 2.5 Four Policy briefs and working papers for investments in seed, soil fertility management, and machinery for sustainable and resilient maize sector developed. | Mahesh | Powell , Sagar, Ravi, Alison, Sreejith, Owen
Work package 2: Farm Productivity Improvement | 2.6 Develop the working paper on good agronomic management practices (efficient water and nutrient management) and restore soil health for sustainable and resilient targeted maize production systems. |  | Mahesh | Saiful, Faisal, Alison,Sagar
Work package 2: Farm Productivity Improvement | 2.7 Identify options for diversified and resilient production systems by intercropping with legumes and determine suitability for additive intercropping with different intercrops in different agroecologies across Nepal, Bangladesh, India. | 2.5 A working paper on performance of inter-cropping configurations across agro-ecologies to enhance diversification and resilience of maize sector developed. | Alison | Sonam, Powell, Sagar, Pankaj | [7 empty] | Design | Design & Data | Data | Data | Models | Analysis | Report | Report
Work package 2: Farm Productivity Improvement | 2.8 Conduct TOTs on seed, soil fertility and irrigation management bundles with private actors, extension agents and lead farmers, involving women, men, and young people among both trainers and trainees, for improved maize production in 20,000 ha in Nepal | 2.8 Farmers increase yield by 20%, on average, compared to baseline 2020 in Nepal. 2.7 About 20,000 women, men, and young farmers, in proportions reflective of their population sizes, benefit from improved maize production technologies in Nepal. | Dyutiman | Narayan, Sagar, Pankaj
Work package 2: Farm Productivity Improvement | 2.9 Implement CIMMYTs e-agrology digital platform for monitoring maize production, assessing cost benefits and marketing in two pilot sites of Nepal | 2.6. Cost benefit of improved maize technology application evaluated through the e agrology platform | Dyutiman | Narayan, Sagar, Pankaj
Work package 2: Farm Productivity Improvement | 2.10 Develop investment roadmaps for the private sector for localized seed systems, improved mechanization services, and efficient fertilizer management for Bangladesh, India and Nepal. | 2.5 Five Policy briefs and working papers for investments in seed, soil fertility management, inter-cropping and machinery for sustainable and resilient maize sector developed. | Ravi | Dyutiman, Amjath, Sreejith, Bharathi, Owen, Mahesh
Work package 3: Integrated maize seed systems innovations and transformation |  |  | Abdu
Work package 3: Integrated maize seed systems innovations and transformation | 3.1 Strengthen seed companies capacity for compliant hybrid seed production, seed certification, and seed business management | 3.1 Digitally enabled national seed information systems piloted in Bangladesh, the Philippines, and Nepal, incorporating AI-enabled features and interoperability with existing public and private digital platforms. | Abdu (...) | Zaidi, Nick, Aparna, Remy, DESIS consultant, LRS consultant: Bharathi; Bangladesh LRS-2
Work package 3: Integrated maize seed systems innovations and transformation | 3.2 Assess the status of maize seed systems across the Indo-Pacific to identify gaps, inform policy dialogue, and support harmonization of regulatory and operational approaches across the region. | 3.2 Conduct at least three orientation and validation workshops on the digitally enabled seed information system to familiarize end users and validate functionality and usability. | Abdu | Zaidi, Nick, Aparna, Remy, DESIS consultant, LRS consultant:
Work package 3: Integrated maize seed systems innovations and transformation | 3.3 Develop and enhance interoperable digital seed information system for varietal tracking, seed demand-supply analysis, and data driven varietal choices by end users in Bangladesh, Nepal and Philippines. | 3.3 At least three national-level and two regional-level technical training and experience-sharing events are conducted to strengthen capacities across maize seed system stakeholders. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant:
Work package 3: Integrated maize seed systems innovations and transformation | 3.4 Facilitate regional dialogue among regulators, seed companies, and seed trade associations to reduce barriers to cross-border seed production and trade. | 3.4 One regional policy and market dialogue convened to facilitate maize seed trade and regulatory coordination across the Indo-Pacific. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant:
Work package 3: Integrated maize seed systems innovations and transformation | 3.5 Provide training and ongoing support to women, men, and young people engaged in seed production, distribution, and use to strengthen digital skills needed to access and apply information from digital seed information systems and related platforms. | 3.5 A comprehensive Indo-Pacific maize seed systems status report produced to inform policy, investment, and future program design. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (6), Bharathi, Dyutiman
Work package 3: Integrated maize seed systems innovations and transformation | 3.6 Organize tailor-made training for NARS and seed companies on quality seed production and seed business management in Bangladesh, India, Nepal and Philippines. | 3.6 Seed system innovations will reflect demand signals and varietal choices of farmers across target markets. | Abdu | Zaidi, Nick, Aparna, Remy, IRS consultant, LRS consultant (6):
Work package 3: Integrated maize seed systems innovations and transformation | 3.7 Support NARS and national seed companies to improve seed demand forecasting, multiplication planning, and quality assurance through innovative seed systems tools. |  | Abdu | Zaidi, Nick, Aparna, Remy, IRS consultant, LRS consultant (6):
Work package 4: Market Development and Access |  |  | Dyutiman
Work package 4: Market Development and Access | 4.1 Document emerging changes in the maize market systems (food, feed, silage and biofuels) in the Indo Pacific region and key drivers of growth influencing maize value chain dynamics on production, processing, and marketing to inform pro-commercialization development interventions. | 4.1 A “Maize for Asia” report on CIMMYT contributions, production and market trends and future outlook prepared and shared among maize sector stakeholders in the region 4.2 Five National maize value chain reports with recommendations for scaling and investment options shared | Dyutiman | Zaidi, Ravi, Adeeth, Sreejith, Mahesh, Narayan, Pankaj, Abdu
Work package 4: Market Development and Access | 4.2 Consolidate and upgrade CIMMYT Nepal’s digital platforms (krishiprabidhi.net) to function as maize data warehouse and facilitate data analysis, and explore AI-based applications with Ag Tech startups for improved maize market information systems. | 4.3 A national level maize data warehouse developed for facilitating Ag extension in Nepal | Dyutiman | Sreejith, Narayan, Pankaj, Sagar, Satish
Work package 4: Market Development and Access | 4.3 Provide business mentorship support through multi stakeholder platforms, facilitate farmer market linkages and market coordination mechanisms by connecting women, men, and young farmers with food and feed industries to develop remunerative, inclusive and resilient supply chains in Nepal’s terai | 4.4 Investments up to USD 3 M mobilized from public and private sectors for maize commercialization in Nepal | Dyutiman | Narayan
Work package 4: Market Development and Access | 4.4 Organize investment forums, agricultural innovation exchange platforms and agro input fairs with private public partnerships to boost investments and the delivery of quality ag inputs to farmers. | 4.5 TwoProposals developed with the evidence from this activity submitted to donors funding in 2026 and beyond 4.6 An operational innovation exchange platform linking global innovation providers (including US based actors) with stakeholders in the Philippines and Indonesia | Amjath | Sreejith, GMP colleagues from Philippines
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) |  |  | Abdu
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.1 Upgrade CIMMYT’s seed hub at Nepalgunj to meet regional EGS demand and enable the timely dispatch of at least 5–10 shipments to partner countries across South and Southeast Asia. | 5.1 CIMMYT Nepalgunj seed hub upgraded and operational as a regional EGS hub, with enhanced capacity to produce EGS, hybrid and inbred line seed for South and Southeast Asia. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.2 Establish standardized EGS seed storage, seed conditioning facilities, cold chambers, and inventory management systems to support multi-country dispatch. | 5.2 High-standard seed storage, seed conditioning facilities, cold chambers, inventory management, and phytosanitary compliance systems established for seed dispatch requirements in target countries. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.3 Produce and supply parental seeds for priority CIMMYT maize hybrids aligned with regional breeding pipelines. | 5.3 Parental seed of priority CIMMYT maize hybrids produced and supplied in alignment with regional breeding pipelines and partner demand, supporting timely hybrid deployment. | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.4 Strengthen phytosanitary compliance, documentation, and seed movement protocols aligned with regional regulations. | 5.4 A replicable, best-practice EGS infrastructure and service delivery model demonstrated | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.5 Demonstrate best-in-class EGS infrastructure for replication by regional partners. |  | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) | 5.6 Provide scientific and technical capacity strengthening to NARC and Nepal’s hybrid maize program by ensuring reliable access to EGS, along with other maize-based seed technologies. |  | Abdu | Zaidi, Nagesh, Nick, Aparna, Remy, IRS consultant, LRS consultant (3):

## Work Package Level
Work Package | Key Activity | Activity lead | Operations US$ | Co-Financing in 2026 US$ | Co-Finance sources | Possible Future Funding US$ | Future funding sources | Notes
Work package 1: Strengthening Regional and Scientific Cooperation |  |  | 245100 | 0 |  | 0
| 1.1 | Zaidi | 210300 | NA | NA | 1.5M | ADB | To be pursued
| 1.2 | Zaidi | 34800 | NA | NA | 0.5M | ADB | To be pursued
| 1.3 | Adeeth
| 1.4 | Dyutiman
| 1.5 Regional Dashboard | Satish | 15000
Work package 2: Farm Productivity Improvement |  |  | 914591
| 2.1 | Zaidi | 408901 | 120000 | B4T | 1.0M | BMGF, Green Climate Fund | To be pursued
| 2.2 | Zaidi | 246500 | 75000 | Philippines contribution | 1.7M | Mastercard foundation | To be pursued
| 2.3 | Zaidi | 195600 | 35000 | DH service fund | 0.5M | DBT, Govt. of India | To be pursued
| 2.4 | Zaidi | 63590 | 20000 | CAMSA | 0.5M | B4T | To be pursued
| 2.5-2.6 | Mahesh
| 2.7 | Alison
| 2.8 e-Agorlogy | Satish | 22000 | 98000
| 2.9 | Dyutiman
| 2.10 AgroTutor AI Advisory | Satish | 36000
| 2.10 | Ravi
Work package 3: Integrated maize seed systems innovations and transformation |  |  | 982304
| 3.1 | Abdu | 180000 | 84000 | Philippines contribution | 1.8M | ADB | ADB Proposal for Nepal
| 3.2 | Abdu | 75000 |  |  |  | WB, GCF
| 3.3 | Abdu | 175000
| 3.4 | Abdu | 80000
| 3.5 | Abdu | 25000
| 3.6 | Abdu | 20000
| Personnel, cosnultants, and LRS | Abdu | 260300
| S&S, travels and others | Abdu | 167004
Work package 4: Market Development and Access
| 4.1-4.3 | Dyutiman
| 4.2: Open Maize Data Exchange | Satish | 25000
| 4.4 | Amjath
Work package 5: CIMMYT Nepalgunj Regional Early Generation Seed (EGS) |  |  | 676730
| 5.1 | Abdu | 25000 |  | In kind contribution by GoN |  |  | 6.0ha lease land allocated to CIMMYT by GoN free of cost
| 5.2 | Abdu | 400000 |  | In Kind contribution by GoN | Proposed as part of CIMMYT Inc to generate resources based on cost recovery through the delivery of EGS and hybrid seed parental seeds. |  | 6.0ha lease land allocated to CIMMYT by GoN free of cost
| 5.3 | Abdu | 25000
| Personnel, cosnultants, and LRS | Abdu | 167300
| S&S, travels and others | Abdu | 59430
MEL: Monitoring, Evaluation and Learning (HQ) |  |  | 64500
| MEL 1. Personnel (IRS) | Andrea and Syed | 22500
| MEL 2. Personnel (LRS) | MEL LRS (BD/NP) | 12000
| MEL 3. Survey and consultants |  | 15000
| MEL 4. Travel |  | 15000
SUMMARY | GMP | 2818725
SAS

## Sheet1
Year 1
Type | Name | Position | Location | Level | FTE | SALARY | MOS | TOTAL
IRS10 | New hire | Maize Breeder | Hyderabad |  | 35% | 185000 | 12 | 64750
IRS12 | P. Zaidi | Maize Physiologist and Breeder - Asia | Hyderabad |  | 20% | 253000 | 12 | 50600
IRS11 | A. Issa | Seed System | Nepal |  | 50% | 196000 | 12 | 98000
IRS13 | A. Saxena | Program Director | Kenya |  | 10% | 377000 | 12 | 37700
IRS12 | A. Das | Sr. Technical Program Manager | Kenya |  | 5% | 253000 | 12 | 12650
IRS11 | N. Davis | Program Manager | Kenya |  | 5% | 196000 | 12 | 9800
IRS11 | R. Labuguen | Finance Manager | Mexico |  | 5% | 196000 | 12 | 9800
LRS01 |  | Field Technician | Hyderabad |  | 100% | 8988 | 12 | 8988
LRS06 |  | Sr. Res. Technician | Hyderabad |  | 50% | 15000 | 12 | 7500
LRS09 |  | Project Scientist | Hyderabad |  | 100% | 46117.65 | 12 | 46117.65
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
[5 empty] | 0% |  | 12 | 0
| Personnel | [6 empty] | 345905.65
| Consultants | [6 empty] | 240000
| Consultant 1 | Senior Level | Bangladesh |  | 100% | 36000 | 12 | 36000
| Consultant 2 | Senior Level | Philippines |  | 100% | 36000 | 12 | 36000
| Consultant 3 | Senior Level | Nepal |  | 300% | 36000 | 12 | 108000
| Consultant 4 | International | Nepal |  | 200% | 30000 | 12 | 60000
| Training and Workshops | [6 empty] | 420500
| Detail 1 |  | India |  |  | 50000 | 1 | 50000
| Detail 2 |  | India |  |  | 40000 | 1 | 40000
| Detail 3 |  | Regional Training |  |  | 80000 | 1 | 80000
| Detail 3 |  | Nepal/Bangladesh/ Philippines |  |  | 58500 | 3 | 175500
| Detail 4 |  | Nepal/Bangladesh/ Philippines |  |  | 25000 | 3 | 75000
| Other Supplies and Services | [6 empty] | 472000
| Detail 1 |  | India |  |  | 382000 | 1 | 382000
| Detail 2 |  | Nepal |  |  | 90000 | 1 | 90000
Detail 3
| Partners | [6 empty] | 310000
| Partner 1 |  | India |  |  | 25000 | 1 | 25000
| Partner 2 |  | India |  |  | 20000 | 1 | 20000
| Partner 3 |  | India |  |  | 20000 | 1 | 20000
| Partner 4 |  | India |  |  | 20000 | 1 | 20000
| Partner 6 |  | DESIS-Nepal/Phillipines/Bangladesh |  |  | 180000 | 1 | 180000
| Partner 7 |  | Bangaldesh |  |  | 20000 | 1 | 20000
| Partner 8 |  | Philippines |  |  | 25000 | 1 | 25000
| Equipment | [6 empty] | 505000
| Equipment 1 |  | India |  |  | 50000 | 1 | 50000
| Equipment 2 |  | Nepal |  |  | 455000 | 1 | 455000
Equipment 3
| Travel | [6 empty] | 160000
| Detail 1 |  | India |  |  | 60000 | 1 | 60000
| Detail 2 |  | Nepal/Bangladesh/Philippines |  |  | 100000 | 1 | 100000
Detail 3
| Chargebacks | [6 empty] | 100816.8632
| ICT | [6 empty] | 15917.4366
| Non windows |  |  |  | 444.8462 |  | 0 | 0
| Standard scientist |  |  |  | 349.0666 | 380% | 12 | 15917.4366
| GARS |  |  |  | 858.0803 | 1 | 12 | 10296.9637
| Knowledge Center |  |  |  | 196.3368 | 130% | 12 | 3062.8546
| Regional Office Shared Cost | [6 empty] | 32755.6084
| Bangladesh |  |  |  | 461.396 |  | 0 | 0
| India |  |  |  | 788.4003 | 305% | 12 | 28855.4522
| Nepal |  |  |  | 512.426 | 50% | 12 | 3074.5562
| Kenya |  |  |  | 344 | 20% | 12 | 825.6
| Other RO |  |  |  | 0 |  | 0 | 0
| Fleet | [6 empty] | 38784
| Pick up - Nepal |  |  |  | 1616 | 200% | 12 | 38784
| Total Direct Costs | [6 empty] | 2554222.5132
| Indirect Cost | [5 empty] | 15% | 336633.377
| Flow-through | [5 empty] | 5% | 15500
| Total Indirect costs | [6 empty] | 352133.377
| Sub-TOTAL | [6 empty] | 2906355.8902
| CGIAR fee | [6 empty] | 58127.1178
| TOTAL | [6 empty] | 2964483.008
| #REF! | $1,159,740.00
49